## Workplan
Lents Stabilization and Job Creation Collaborative
Project Work Plan - Draft 2016-09-27
|  | FY 2016-2017 |  |  |  | FY 2017-2018 |  |  |  | Dependencies
ID | Program/Task | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Incoming | Outgoing
1.0 | Residential Stabilization
1.1 | Social Conditions
1.1.1 | Vulnerability Analysis | bar: FY 2016-2017 Q4 to FY 2017-2018 Q1
1.1.2 | Resident Survey | bar: FY 2016-2017 Q4 to FY 2017-2018 Q1
1.2 | Neighborhood Conditions
1.2.1 | Floodplain Impacts (SFR) | [8 empty] | 3.6 | 3.7 | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
1.2.2 | Floodplai Impacts (MFR) | [8 empty] | 3.6 | 3.7 | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
1.2.3 | FEMA NFIP Rate Methodolgy | [8 empty] | 3.6 | 3.7 | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
1.2.4 | Flood Risk Cost/Impact Assessment | [8 empty] | 3.6 | 3.7 | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
1.3 | Final Deliverables - Analytical Products
1.3.1 | Qualitative Analysis - Two Scenarios | bar: FY 2017-2018 Q3
1.3.2 | Estimated Costs and Benefits | [8 empty] | 4.2 | bar: FY 2017-2018 Q3
1.4 | Near-Term Strategies
1.4.1 | LOMA Assistance Program | bar: FY 2016-2017 Q2 to FY 2017-2018 Q4
1.4.2 | Three-Year Displacement Program | bar: FY 2016-2017 Q2 to FY 2017-2018 Q4
1.4.3 | Floodplain 101 | bar: FY 2016-2017 Q2 to FY 2017-2018 Q4
1.4.4 | Direct Assistance Program | bar: FY 2016-2017 Q2 to FY 2017-2018 Q4
1.5 | Long-Term Strategies
1.5.1 | Analyze FEMA Map Problems (LOMA/LOMR) | [8 empty] | 3.7 | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
1.5.2 | CoP Flood Risk Self-Insurance Program | [8 empty] | 3.7 | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
1.5.3 | Alternative Flood Insurance Strategies | [8 empty] | 3.7 | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
1.5.4 | Housing Displacement Strategies (Flood Bank) | [8 empty] | 3.7 | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
1.5.5 | Organizational and Administrative Options [Internal to Housing] | [8 empty] | 3.7 | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
1.5.6 | Neighbor Stabilization Lessons applied Citywide | [8 empty] | 3.7 | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
1.5.7 | Near-Term NFIP Costs Reduction Strategies | [8 empty] | 3.7 | bar: FY 2016-2017 Q2 to FY 2017-2018 Q4
1.5.8 | Displacement Strategies - Post-Map Change | [8 empty] | 3.7 | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
1.5.9 | Recommendations: Long-term Project Governance/Administration - See Task 4.0
2.0 | Industrial Site Readiness
2.1 | Assess Existing Conditions
2.1.1 | SWOT Analysis of East Foster Industrial Area | bar: FY 2016-2017 Q4 to FY 2017-2018 Q1
2.1.2 | Site Conditions - Review Soils/Contaminants Report | bar: FY 2016-2017 Q4 to FY 2017-2018 Q1
2.1.3 | Assess Costs/Impacts of Raising Foster Road | [8 empty] | 3.5 | 3.6, 3.7 | bar: FY 2016-2017 Q4 to FY 2017-2018 Q1
2.1.4 | Align Local, State and Federal Site Readiness Support | bar: FY 2016-2017 Q4 to FY 2017-2018 Q1
2.1.5 | Report: Inventory, Conditions, Barriers to Development | [8 empty] | 3.5 | 3.6, 3.7 | bar: FY 2016-2017 Q4 to FY 2017-2018 Q1
2.1.6 | Report: Available Resources for Readiness Initiatives | bar: FY 2016-2017 Q4 to FY 2017-2018 Q1
2.2 | Concept Development
2.2.1 | Develop Scenarios to increase Industrial Capacity | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
2.2.2 | Develop an East Foster Master Plan | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
2.2.3 | Report: Scenarios to implement Site Readiness Initiative | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
2.3 | Final Deliverables
2.3.1 | Recommendations: Site Readiness/Job Creation Program | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
2.3.2 | Analysis of Costs/ Benefits of Recommendations | [8 empty] | 4.2 | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
2.3.3 | Next Steps for Program Implementation | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
2.3.4 | Recommendations: Long-term Project Governance/Administration - See Task 4.0
3.0 | Floodplain Mitigation Bank
3.1 | Assess Floodplain Conditions
3.1.1 | Flood Inundation Map - Modeing Flood Impacts | bar: FY 2016-2017 Q2 to FY 2016-2017 Q3
3.2 | Regulatory Framework
3.2.1 | Summarize Relevant Regulations | bar: FY 2016-2017 Q2 to FY 2016-2017 Q3
3.2.2 | Review CoP Streamlining Committee Process | bar: FY 2016-2017 Q3
3.3 | Ecological Conditions
3.3.1 | Inventory Ecological Functions and Values | bar: FY 2016-2017 Q3 to FY 2016-2017 Q4
3.3.2 | Review FEMA Cost/Benefit Analysis Protocol | bar: FY 2016-2017 Q3 to FY 2016-2017 Q4
3.3.3 | Review Soils/Contaminants Report | bar: FY 2016-2017 Q3 to FY 2016-2017 Q4
3.3.4 | Determine Mitigation Requirements (Current Regulations) | bar: FY 2016-2017 Q3 to FY 2016-2017 Q4
3.4 | Climate Change
3.4.1 | Assess Potential Climate Change Impacts (near-term) | bar: FY 2016-2017 Q4
3.4.2 | Assess Potential Climate Change Impacts (long-term) | bar: FY 2016-2017 Q4
3.5 | Economic Impacts
3.5.1 | Economic Impacts of Flood Risks on Industrial Lands | bar: FY 2016-2017 Q4 to FY 2017-2018 Q1
3.5.2 | Economic Value of removal from Flood Hazard Map | bar: FY 2016-2017 Q4 to FY 2017-2018 Q1
3.5.3 | Imacts of Other Impediments to Development | bar: FY 2016-2017 Q4 to FY 2017-2018 Q1
3.5.4 | Impact of Providing Fill, Site Prep and Permitting Assistance | bar: FY 2016-2017 Q4 to FY 2017-2018 Q1
3.6 | Final Products - Assessments
3.6.1 | Permitting Requirments to enable Fill | bar: FY 2017-2018 Q1 to FY 2017-2018 Q2
3.6.2 | Assessment of Benefit/Challenges of Project Implementation | bar: FY 2017-2018 Q1 to FY 2017-2018 Q2
3.6.3 | Economic/Ecological/Mitigation Potential of Flood Mitigation Bank | bar: FY 2017-2018 Q1 to FY 2017-2018 Q2
3.7 | Concept Development
3.7.1 | Criteria/Methodology for Selecting/Prioritizing Flood Storage Sites | bar: FY 2017-2018 Q2
3.7.2 | Develop Draft Regional Cut and Fill Process | bar: FY 2017-2018 Q2
3.7.3 | Analyze Environmental, Economic and Social Benefits
3.7.3.1 | Financial - Economic Value, Private/Public Investors, Funding Sources | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
3.7.3.2 | Environmental - Water Quaity, Hydrology, Habitat | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
3.7.3.3 | Social - Impacts to Property Ownership, Natural Areas, Neighborhood | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
3.7.4 | Test Concepts with Stakeholders | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
3.7.5 | Develop Construction Sequencing Strategies | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
3.7.6 | Assess the Feasibility of using Soils for Fill | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
3.7.7 | Organizational/Administrative Approaches | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
3.7.8 | Assess Potential Application of Strategies for the City and Region | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
3.8 | Final Procuts - Concept Development
3.8.1 | Recommendations and Next Steps to create a Flood Mitigation Bank | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
3.8.2 | Financial Implications of the Flood Mitigation Bank | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
3.8.3 | Recommendations: Long-term Project Governance/Administration | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
4.0 | Governance & Finance
4.1 | Assess Conditions - Governance
4.1.1 | Assess Potential Roles of Existing Organizations | bar: FY 2017-2018 Q1 to FY 2017-2018 Q2
4.1.2 | Research Organizational Models | bar: FY 2017-2018 Q1 to FY 2017-2018 Q2
4.1.3 | Compile Governance/Finance Recommendations (1.5.9/2.3.4/3.8.3) | bar: FY 2017-2018 Q1 to FY 2017-2018 Q2
4.1.4 | Identify Common Needs and Potential Conflicts | bar: FY 2017-2018 Q1 to FY 2017-2018 Q2
4.2 | Assess Conditions - Finance
4.2.1 | Assess Potential Funding and Financing Strategies | bar: FY 2017-2018 Q1 to FY 2017-2018 Q2
4.2.2 | Quantify Financial Requirements | bar: FY 2017-2018 Q1 to FY 2017-2018 Q2
4.2.3 | Identify Potential Funding Sources | bar: FY 2017-2018 Q1 to FY 2017-2018 Q2
4.2.4 | Research Funding Models | bar: FY 2017-2018 Q1 to FY 2017-2018 Q2
4.3 | Final Products - Assess Conditions
4.3.1 | Summarize organizational models of long-term governance | bar: FY 2017-2018 Q2
4.3.2 | Summarize existing and potential funding sources | bar: FY 2017-2018 Q2
4.4 | Concept Development - Governance
4.4.1 | Develop alternative long-term governance strategies | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
4.4.2 | Evaluate goverance strategies | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
4.4.3 | Select preferred governance strategy | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
4.5 | Concept Development - Finance
4.5.1 | Develop alternative long-term financing approaches | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
4.5.2 | Evaluate financing approaches | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
4.5.3 | Select preferred financing approach | bar: FY 2017-2018 Q2 to FY 2017-2018 Q3
4.6 | Final Products - Concept Development
4.6.1 | Recommendations: Long-Term Governance and Finance Strategies | bar: FY 2017-2018 Q3 to FY 2017-2018 Q4
5.0 | Communications and Outreach